Scope of Work for Engineering of Hook up of LP Compressor Package

Doc. No. MUM-SPO-OPS-SOW-0001

| A1 | 18 May 2023 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Rev | Date | Description | Prepared | Reviewed | Approved |

Table of Contents

1.0	INTRODUCTION	3

1.1	PROJECT BACKGROUND	3

1.2	DEFINITIONS	4

1.3	ABBREVIATIONS	4

2.0	SCOPE	5

3.0	EXECUTION METHODOLOGY	7

3.1	KICK OFF	7

3.2	DETAIL ENGINEERING	7

3.3	PROCUREMENT ASSISTANCE	7

3.4	COMMISSIONING ASSISTANCE	7

4.0	ENGINEERING AND PROJECT MANAGEMENT	7

4.1	Project Management, Coordination and Control	7

4.2	Supervision	8

4.3	INTERDISCPILINARY REVIEWS	8

4.4	INTERFACE MANAGEMENT	8

4.5	DOCUMENT MANAGEMENT	8

4.6	SCHEDULE MANAGEMENT	8

4.7	Progress Monitoring and Measurement	9

4.8	Document managEment system	10

4.9	Communication	10

4.10	PROJECT MEETINGS	10

5.0	DESIGN ASSURANCE PROCESS	11

5.1	Filing and Archiving	11

6.0	PROJECT IMPLEMENTATION PLAN	12

6.1	EXECUTION POLICIES	12

7.0	PROJECT ORGANIZATION	13

7.1	Roles and Responsibilities	13

8.0	ASSUMPTIONS AND EXCLUSIONS	15

ANNEXURE-1 DETAIL ENGINEERING FOR LP GAS MONETISATION FOR NBP-FPSO, B&S ASSET - DELIVERABLE REGISTER	16

# INTRODUCTION

## PROJECT BACKGROUND

Oil and Natural Gas Corporation Limited (OPGC) is engaged in exploration & processing of hydrocarbon at the NBP(D1) field is located about 200 km to the west of Mumbai city in the Western Offshore area at a water depth of 85 to 100 meters. The field was developed in four phases. Presently, the field is being exploited through 39 oil producers from 5 WHP (NBP- A, B, C, D & E) platforms. Water injection is being done through 3 wells at an average rate of 12800 BWPD. The current rate of production from the field is about 22500 barrels of oil.

At present, well fluid (WF) lines from NBP-C, NBP-D and NBP-E are brought directly to the subsea PLEM through subsea jumper lines at downstream of NBP-B platform and combined well fluid (including NBP-A & NBP-B) is transported to Floating Production Storage and Offloading (FPSO) via subsea WF manifold. FPSO is deployed to process and temporarily store the well fluid from entire NBP field.

Shapoorji Pallonji Armada Oil and Gas Services Private Limited (SPAOG) a joint-venture company between Shapoorji Pallonji (India) and Bumi Armada Berhad (Malaysia) operates FPSO Armada Sterling at NBP(D1) field to produce hydrocarbon.

Currently, Low pressure gas from LP separator at FPSO in NBP field, B&S Asset gets flared as there is no provision to boost the gas pressure for usage as fuel gas. Shapoorji Pallonji Armada Oil and Gas Services Private Limited intends to install compressors to utilise this flared gas as fuel gas for Boilers/TG which will also result in reduction in consumption of diesel being used presently.

## DEFINITIONS

The following words and expressions shall have the meanings hereby assigned to them except where the context otherwise requires.

| COMPANY | Shall mean the Shapoorji Pallonji Oil and Gas Services Private Limited. |
| --- | --- |
| CONTRACTOR | Shall mean the CONTRACTOR contracted to supply the WORK as set out in the CONTRACT.). |

## ABBREVIATIONS

| BWPD | Barrels of Water Per day |
| --- | --- |
| DCC | Document Control Centre |
| DCS | Distribution Control System |
| EERA | Escape, Evacuation and Rescue Analysis |
| EPC | Engineering Procurement and Construction |
| ESD | Emergency Shutdown |
| FPSO | Floating Production Storage and Offloading |
| GAD | General Arrangement Drawing |
| HMB | Heat Mass Balance |
| HSE | Health Safety and Environment |
| IP | Interface Points |
| MDR | Master Document Register |
| MOC | Management of Change |
| MTO | Material Take off |
| NBP Field | NB Prasad Field |
| OEM | Original Equipment Manufacturer |
| ONGC | Oil and Natural Gas Corporation Limited |
| PFD | Process Flow Diagram |
| PLC | Program Logic Control |
| PLEM | Pipeline End Manifold |
| PSV | Pressure Safety Valve |
| QRA | Quantitative Risk Assessment |
| SLD | Single Line Diagram |
| SPAOG | Shapoorji Pallonji Armada Oil and Gas Services Private Limited |
| TBE | Technical Bid Evaluation |
| TG | Turbine Generator |
| WF | Well Fluid |
| WHP | Wellhead Platform |

# SCOPE

The scope of services is performing detail engineering for the supply installation and commissioning of LP compressor package and hook up with existing system at NBP (D1) field FPSO Armada Sterling. In order to complete the project of LP gas monetization for FPSO engineering Contractor shall perform below engineering activities under the detail engineering,

- Conceptualization of scheme / study for revamp /refurbishment/replacement / debottlenecking, optimization of Processing facilities, Production System configuration and preparation of Project report

- Pre engineering survey to ascertain exact scope of work for the specific project after ascertaining adequacy checks of existing facilities, if any like engineering and system integration with existing systems / facilities

- Complete design and engineering of all the modifications in accordance with Feasibility study  provided by FPSO company and  as  per  requirement for  installation and  commissioning of  compressor package

- Development of Construction design & drawings, PFD, HMB, P & ID, Package data sheet,  cause & effect and other process deliverables

- If needed, visit FPSO facility to finalize detailed design / spool drawings / fabrication drawings, as required by fabrication contractor.

- To check the adequacy of existing flare header and sizing. Fire protection and loss prevention as required to be done.

- Fire & Gas study for coverage has to be included

- Fire water system design and drg ( deluge , Fire water demand etc to be update )

- RAM Study to be conducted (Can be by method of differences with respect to current RAM Study)

- All process Sizing calculations such as PSV sizing

- Update of Existing utilities deliverables, as required not limited to Adequacy check and reports

- Utility requirement list

- Preparation / review of Hazardous Area Classification Drawings Technology scouting and recommending adoption of upgraded technology, material selection, etc. following worldwide industry trend.

- Study of Safety and Safety Systems related to the Projects.

- Development of Equipment layout and Piping Layout along with piping support design and drawings, including Stress analysis.

- Development of PMS and VMS

- Piping stress analysis

- Structural analysis of Deck, pipe support, process columns, modules, etc.

- Table top design / stool base for skid installation.

- Suitability assessment regarding Vendor / Service Provider / Construction Equipment etc.

- Instrumentation sizing calculations

- Development of Cause & Effect Matrices

- Preparation of Material requisition and Purchase specification

- Development of Isometric drawing

- Development of Project BOQs and MTO

- Preparation of engineering architecture for DCS /ESD PLC of control system (DCS up gradation/revamping.

- All Instrumentation and Telecom deliverables required for the defined scope

- Escape Route update at the location this new LP compressor package

- Fire Water Hydraulic and Transient Study;

- Escape, Evacuation and Rescue Analysis (EERA) Update

- Quantitative Risk Assessment (QRA) Update

- Electrical deliverables development

  - Electrical load list to be updated,

  - Electrical load assessment to be updated

  - New cable tray and supports will be provided for the routing near the skid.

Note: 	Existing spare feeders shall be checked. There are other auxiliaries for the compressor with drives and those shall be also checked.

Modifications to be carried out in the switchgear will be studied including relevant analysis of generator capacity, etc.

- Feeder sizing and control loop diagram development

- Preparation of scope of document for a specific project based on the latest technology after finalization of site / environmental data, design basis, criteria, sizing criteria, material of construction selection criteria, related functional specifications and scope of work and following international codes / standards and best in class practices complying with necessary statutory requirements for execution of the project on EPC, LSTK basis or any other manner.

- Preparation of Technical Evaluation Report based on Bid specification and Technical Bid Evaluation Criteria (if required).

- Review and approval of OEM deliverables

- Development of execution methodology

- Development of Shutdown Methodology

- HAZOP Study

- Assistance in preparing price schedule, Milestone payment formulae & allotting weighted factors to project execution activities by LSTK contractor.

- Preparation of list of probable bidders and assistance in finalization of contractor qualification criteria (based on sound credential)

- Review recommendation of qualification document on construction / installation

- equipment’s.

- Supervision of field activities (during commissioning offshore) as well as Participation during Factory acceptance test (FAT)

- Preparation of Project quality plan

- Installation methodology development

- Contractor shall be responsible for CLASS Design approval.

- CRS (Comments Response sheet), meetings, CLASS Comments shall be EP Responsibility

- Contractor to mobilize Engineers for Machineries and fabricated item Inspection as per Approved Drg at Vendor Facility as Optional Scope.

# EXECUTION METHODOLOGY

## KICK OFF

Project Kick Off Meeting shall be carried out with CLIENT for discussion in detail post receipt of CLIENT inputs.

## DETAIL ENGINEERING

Contractor shall develop all engineering deliverables as per attached Deliverable list for completeness of engineering activities for procurement and installation commissioning and hook up of LP compressor package at FPSOs. To include TBE, VDR, VDI and As-built portion.

Exclusion:

- Feasibility study for installation of package

- Overall FPSO stability analysis

- PDMS Admin Hours.3d Model Database Preparation Hours

- 3d Modeling

## PROCUREMENT ASSISTANCE

Contractor shall assist to develop all the procurement deliverables including MR and Purchase specification for approval.

## COMMISSIONING ASSISTANCE

The Contractor shall deploy engineering personnel as per client instruction to assist during commissioning and site installation.

# ENGINEERING AND PROJECT MANAGEMENT

## Project Management, Coordination and Control

An overall project management framework for successful completion of the service will be implemented to cover, among the others, the following areas:

- Detail design supervision and interfacing.

- Planning and schedule.

- Document control.

- Progress measurement and monitoring.

- HSE.

- Preparation of progress reports.

- Logistic and facilities.

Contractor will ensure that all parties involved in the Service will be properly coordinated and that interfaces will be dealt with in a prompt manner.

## Supervision

Project management aims managing properly the Service, monitoring the progress of activities in compliance with the deadlines established by  Contractor/Client and representing the only interface for the communication between Client and  Contractor,  in  order  to  optimize  the  data  and  information  flow  and  the  necessary  takeover  of responsibilities.

## INTERDISCPILINARY REVIEWS

The internal disciplinary reviews will be carried out internally as per the Quality Procedures

## INTERFACE MANAGEMENT

The Interface Management will be a continual activity with the compliance to all the interface points (IP) with tag numbers, elevations, MOC, services and coordinates Monthly Interface Meetings will be carried with a dedicated Interface team.

## DOCUMENT MANAGEMENT

All formal communications and agreements including invoicing and payments are to be between M/s   Project Manager and Client’s representative. All incoming and outgoing correspondence shall be routed through Document Control Centre (DCC). All formal correspondence like transmittals, faxes and letters originating from M/s   and COMPANY are to be assigned a sequential /Contractor identification number and logged in the correspondence log by the Project administrator/Document Controller.   will provide a communication matrix for the Project. The transmittal of deliverable documents and reports to clients (i.e. drawings, reports and specifications) shall be transmitted only through the Document Controller using Document Control Centre (DCC).

## SCHEDULE MANAGEMENT

A complete Project Development Plan (PDP) will be prepared including all activities, deliverables and dates; the plan will be adjusted and amended from time to time to suit the evolution of the Project.

The Contractor will prepare a detailed schedule, comprising all main activities that are expected for the execution of the Project. The scheduling between the various activities will be realized by the use of logical links.  The contractor will ensure that the majority of the tasks have predecessors and successors.

Permitting activities leading to the receipt of various administrative authorizations shall be provided by the Owner as well as relevant constraints to the schedule.

Schedule Management will be a continual activity with the compliance to Construction requirement and Procurement Management and requirement.

Weekly Schedule Management Meetings will be carried with a dedicated Project Controller and shall manage the overall Engineering Progress.

The Schedule Management will be carried out vide MS Project / Primavera P6. The Overall Engineering Schedule will be compressed to support the CLIENT on Project Progress Management.

## Progress Monitoring and Measurement

The Project Manager will draw up the monthly progress report of the activities performed by CONTRACTOR showing a detailed progress of the Service as well as additional activities, any deviation from contractual time schedule for service any recovery action should be deemed as necessary.

The monthly report will contain:

- Executive summary.

- Project narrative.

- Progress measurement, schedule and costs.

- Actions proposed to maintain schedule, if any;

- List of propose/accepted variations.

- Identification of critical activities, areas of concern and holds.

- Comparison between actual progress vs. planned one.

Update document register.

The monthly progress report will take into account all activities performed during the month; the report will be issued by Contractor at the end of each month for approval and countersigned, with the necessary annotations, by Company representative within 5 working days from the receipt day.

## Document managEment system

The document control is through the company’s standard procedure and submittals.

Document Control:

All the submission procedure is through an online system for all drawings and quality records from initial engineering stage through construction to final Document Handover. This shall be the main system utilized as per Document Control requirements.

The Document Management procedure shall describe how approval, distribution, filing of masters and deletion/segregation of superseded issues, will be controlled both in hard and soft copies. It shall also describe how review comments, both within CONTRACTOR organization and from COMPANY, shall be transmitted and processed. Electronic data control methods should be used wherever possible.

The system shall provide up to date approval status/tracking of documents, revision control and controlled issue to all parties involved in the WORKS.

## Communication

- Different level of communications will be considered:

- Official communication;

- Work communication.

Official communication will be relevant to transmission of comment sheets and any contractual issues.  Official communication will be made by the Project Manager by official letters.

Work communication will be relevant to discussion of technical issues and will occur through e -mail, phone calls and videoconferences.

Regular meetings for coordination and discussions may be held using  Contractor either face to face or via videoconference system or other systems like “Skype”.

## PROJECT MEETINGS

As part of the coordination activities the following meetings are planned:

| MEETING LOCATION ATTENDEE |  |  |
| --- | --- | --- |
| Kick Off Meeting | Online | Project Manager, Technical Coordinators, Local Team |
| Bi-Weekly / Monthly Meeting | Video Conference | As necessary |

Additional meetings have not been considered in the above table and can be agreed with Client in case of contract award.

# DESIGN ASSURANCE PROCESS

Effective and efficient design interface is of significant importance, and therefore particular focus will be laid on implementation of interdisciplinary checking, design change control and design review.

We will perform the following design assurance activities:

  - Intra-discipline checking (Document check & Lead check prints)

  - Interdisciplinary checking

  - Design change control

  - Design reviews

The controls imposed during the design process would encompass the following:

  - That the design is supported with adequate documentation, analyses and verification.

  - That confirmation is obtained that the design is valid, correct and safe,

  - That unauthorized or un-documented changes to the design are prevented.

## Filing and Archiving

Electronic filing

The system will be set up with a hierarchy that matches the Work Breakdown Structure to facilitate    the search, retrieval and issue of documents according to both the asset or tag number or by the document numbering system.

Hard copy filing

A secure document control area will be set-up in the main project office that will hold all master copies of project documentation (including vendor documentation and superseded revisions of project documents). Retrieval of documents from this store will be managed by the document control group.

Distribution, Timing and Dispatch of Documents Distribution Matrices

Document distribution matrices will be set-up for the project. These documents detail the document types and review cycles required for each document.

Dispatch of Documents (within project team)

CONTRACTOR will utilize the functionality of approved System that will be used for Document Management to distribute documents internally via a registered individually numbered transmittal system. This same process will be used for issue of documentation to vendors / 3rd parties.

Dispatch of Documents (to CLIENT)

CONTRACTOR have implemented a process for managing both the document and data requirements for transfer to CLIENT’s Documentation Issued for Review / Approval.

CONTRACTOR follow strict documentation review processes by which all deliverables must go through a review and approval process, the level of which varies to suit the deliverable type. Sign-off is required at each issued (by originator, checker and approver).

The document distribution matrices will include data on the review process required for each type of deliverable and the distribution required.

These matrices will be reviewed with and approved by CLIENTs to ensure they meet the requirements of all parties. These procedures will also detail the turn-around time for comments on review documents.

# PROJECT IMPLEMENTATION PLAN

## EXECUTION POLICIES

Ethical Code

The main function of the Ethical Code and Code of Conduct is to make the fundamental values and principles which guide the activities of the Companies of the   Group within the organization and to all external interlocutors.

The application of such Code is mandatory for all the personnel of the Contractor including both management and staff personnel and will ensure Client that each Project Team member will individually conduct with the purpose of confirming the image  of correctness,  prestige  and  the  good  reputation which  have always been  assets of  Contractor.  The Ethical Code and Code of Conduct are available upon request.

Quality Assurance

A Quality Manager will be appointed to make sure that documentation quality will meet Contractor and Client requirements. All activities will be performed according to the ISO 9001 certified quality system of Contractor (ISO 9001 certificate is available upon request) and in strict compliance with Contractor’s policy that states that “any service undertaken by   CONSULTING shall be performed to the highest professional level, and shall be carried out in such manner that:

- The Client’s needs and requirements are understood and complied with;

- The results meet professional standards;

- The agreement is fulfilled;

- Environmental, social and health & safety aspects are considered”.

Occupational Health and Safety

All activities will be executed and managed in compliance with certified OHSE management system.

Environmental Management System

All activities will be performed according to the ISO 14001 certified environmental system of Contractor (ISO 14001 certificate is available upon request) and in strict compliance with Contractor’s policy that states that “…  Consulting is committed to establish and continuously improve its own Environmental Management System (EMS), which applies to the operation conducted in its Headquarter, Country Offices and project related operating structures.”

# PROJECT ORGANIZATION

## Roles and Responsibilities

Project Manager

The responsibilities of the Project Manager shall include, but are not limited to, those contained in the following statements:

- Responsible for the overall scope of work within the Project, with specific responsibility for:

  - Review and approval of Engineering methods and procedures,

  - Cost budget management,

  - Equipment / means operations.

- Leading safe behavior and supporting open communication regarding safety issues, Supervision of all personnel seconded to him;

- Direct liaison with Managers/Supervisors who are in-charge of Project services, and who are directly responsible for all personnel/equipment allocated to the Project;

- To be conversant with all items and conditions of the Project both technically and commercially and to have a full understanding of the scope of work.

- Responsible for the implementation, control and monitoring of overall Quality Assurance in all projects related activities as laid down in the Contractor’s Management System (MS);

- Responsible for the preparation and maintenance of budgets for the Project assisted by the Cost Controller.

- Ensuring that the Cost Controller is provided with timely adequate financial information to enable correct and accurate preparation of the accounts and invoices for all activities;

- Responsible for ensuring variations between actual costs and budget are monitored and controlled by the

- Cost Controller, periodically thereafter reviewing the budget for planning and reporting purposes.

- Responsible for identifying and initiating any variations towards the Client or approve/reject variations from third parties on the basis of the contract Terms & Conditions.

- Establish, manage and control the Project Organization defining the line of responsibility to Project personnel and to Department Managers/Supervisors for Project services.

- Liaise with the Client and ensure that Project meetings are held with all relevant personnel during the Project and record same on Minutes of Meeting.

- Liaise with Engineering and ensure Project Design Verification meetings are held with all relevant personnel during the Project and record same on Minutes of Meeting.

- Responsible for establishing resources from departments needed to carry out the Project.

- Ensure that all aspects of Project Administration, Engineering and Operations fulfil the Contract requirements and are conducted in a safe, efficient and profitable manner.

Document Controller

The responsibilities of the Document Controller shall include, but are not limited to, those contained in the following statements:

- Supervise and operate the document management system for the Project.

- Generate and maintain the Project Master Document Register (MDR), ensuring it is up to date at all times.

- Ensure that all documentation is provided as per Contractor format requirements.

- Create and maintain Document Control folders for Project.

- Register all incoming Project documents.

- As instructed by the document author, issue Document Review Register with document details and distribute with document for review. File on completion.

- Assist with preparation of Close Out report for Project Manager.

- Transmittals: ensure all documents and drawings are provided with transmittals when appropriate. Recording document distribution by transmittals. Ensure signed transmittals have been received;

- Complete all electronic Projects archiving as directed by Administration Supervisor.

Discipline Leads

The responsibilities of the Design Lead/Engineering Lead shall include, but are not limited to, those contained in the following statements:

- Responsible for all activities pertaining to the assigned task, as set by the Project Manager;

- Identify and supervise all technical resources needed to complete the task. Assign and coordinate scopes of work, review work done and ensure each resource stays within assigned schedule and cost targets.  Ensure that all personnel under their control are suitably qualified to undertake the work assigned to them;

- Responsible for all engineering activities associated with the task, which shall be reviewed and approved accordingly.  This also includes, but is not limited to, documentation such as Specifications, Procedures, Calculations, Reports, etc.  The Lead Engineer is also responsible for the final dossier.

- Responsible for all interfaces relevant to the task under their responsibility.  This includes, but is not limited to, Client, Subcontractors, Internal Entities etc.;

- Ensure that the Cost Controller/Planner is provided with adequate information to enable correct and accurate preparation of Project status report for the task under their responsibility.

- Responsible for initiating actions to prevent non-conforming condition or product. Initiating, recommending or providing solutions to non-conformances. Verifying the implementation of corrective action and ensuring that these have been effective and controlling further work until the deficiency or unsatisfactory condition has been corrected and the root cause resolved.

- Conduct all activities within the management system, Policy, Procedures and Work Instructions.

- Perform engineering tasks as per Project Engineer, when applicable, in order to complete scopes of work as identified by the Project Manager or Engineering Manager.

- Ensure that the relevant Project Engineers are kept up to date and informed about the direction and methods that the Project engineering is following.

# ASSUMPTIONS AND EXCLUSIONS

- Travel to Site shall be reimbursed at actuals including Man-day Rates to be decided post Award except Pre engineering survey.

- HAZOP chairman shall be deployed by company.

- TPI activities shall be taken care by company.

# ANNEXURE-1 DETAIL ENGINEERING FOR LP GAS MONETISATION FOR NBP-FPSO, B&S ASSET - DELIVERABLE REGISTER

| Sr. No. | Document No. | Document Description | Category |
| --- | --- | --- | --- |
|  |  | PROCESS |  |
| 1 |  | Process Calculation Report | Review |
| 2 |  | Heat and Material Balance Report | Review |
| 3 |  | Equipment List | Review |
| 4 |  | Process Flow Diagram | Review |
| 5 |  | P&ID for Interconnecting P&ID | Review |
| 6 |  | Update P&ID fire water Line | Review |
| 7 |  | Update P&ID Instrument and Utilities | Review |
| 8 |  | Line List | Information |
| 9 |  | Update Cause and Effect | Information |
| 10 |  | Package Process datasheet | Information |
| 11 |  | Update Alarm and trip Schedule | Information |
|  |  | MECHANICAL |  |
| 1 |  | Compressor Package Mechanical Data sheet | Review |
| 2 |  | Functional specification of compressor package | Review |
| 3 |  | MR for compressor package | Review |
| 4 |  | Equipment data sheet | Review |
| 5 |  | TBE & recommendation for Compressor | Review |
|  |  | HSE |  |
| 1 |  | Fire water Hydraulic analysis | - |
| 2 |  | HAZOP Report | Review |
| 3 |  | Update Escape, Evacuation and Rescue Analysis (EERA) Update | Review |
| 4 |  | Update Quantitative Risk Assessment (QRA) Update | Review |
| 5 |  | Layout For Fire Escape Hydrant and Hose Reel System | Information |
| 6 |  | Datasheet For Fire Fighting Equipment’s | Review |
| 7 |  | Update hazardous area classification schedule | Information |
| 8 |  | Update hazardous area classification layout | Information |
| 9 |  | update firefighting & safety equipment layout | Information |
| 10 |  | update fire and gas detection layout | Information |
|  |  | PIPING |  |
| 1 |  | Pipe Wall Thickness Calculation and Report | Review |
| 2 |  | Piping MR | Review |
| 3 |  | Specialty Items List and Datasheet | Review |
| 4 |  | Tie In List | Review |
| 5 |  | Piping GADs and Layouts (Only Annotation, 3D extracted) | Information |
| 6 |  | Update Key Plan Layouts | Information |
| 7 |  | Isometrics | Information |
| 8 |  | Piping Modeling, Trim Modeling | Information |
| 9 |  | Support Modeling | Information |
| 10 |  | Clash Check | Information |
| 11 |  | Model Review | Information |
| 12 |  | Model Review Report | Information |
| 13 |  | MTO | Information |
| 14 |  | Pipe Supports MTO | Information |
| 15 |  | Painting MTO | Information |
| 16 |  | Insulation MTO | Information |
| 17 |  | IDC | Information |
| 18 |  | Vendor Data Review | Information |
|  |  | INSTRUMENTATION & CONTROL |  |
| 1 |  | Material Take-Off for Telecom & Instrumentation |  |
| 2 |  | Instrument Specification - Field Instruments | Review |
| 3 |  | Instrument Specification - Cables | Review |
| 4 |  | Instrument Specification - Package Instruments | Review |
| 5 |  | Datasheet For Field Instruments | Review |
| 6 |  | Datasheet For Fire and Detectors | Review |
| 7 |  | Update Process / F&G Cause & Effect Matrix | Information |
| 8 |  | TBE & recommendation for field instruments | Information |
| 9 |  | TBE & recommendation for cables | Information |
| 10 |  | TBE & recommendation for bulks | Information |
| 11 |  | Update of Alarm and trip schedule | Information |
| 12 |  | TBE & recommendation for Package Instruments | Information |
|  |  | ELECTRICAL |  |
| 1 |  | Detailed Single Line Diagram (LT) | Information |
| 2 |  | Distribution Transformer Sizing Calculation | Information |
| 3 |  | Specification for Switchgear | Review |
| 4 |  | Datasheet for Switchgear (Electrical Datasheet for HV Switchgear) | Review |
| 5 |  | Datasheet for Cables | Review |
| 6 |  | Update Cabling Layout-Trench | Review |
| 7 |  | Cable Schedule | Information |
| 8 |  | Cable Sizing Calculation | Information |
| 9 |  | Earthing Calculation | Information |
| 10 |  | UPS SLD | Information |
| 11 |  | DC Single Line Diagram | Information |
|  |  | CIVIL & STRUCTURAL |  |
| 1 |  | Structural Analysis of Existing Deck Level | Review |
| 2 |  | Compressor Package Foundation Drawing | Review |
| 3 |  | Fabrication Drawing for Compressor Base Frame | Review |
| 4 |  | Analysis and Design of Compressor Base Frame | Review |
| 5 |  | Design Of Pipe Supports | Review |

Notes : Annexure 1 above is a minimum deliverable tabulation . Any activities , deliverables , studies required for the completion of the Scope of work included in this document should be considered as Contractor’s base line SOW, and should be part of LS all inclusive cost .